## Sheet1
Module | Timeline
| Start Date | Finished Date | Days | Developer
Others
Database | 2016-12-12 | 2016-12-13 | 2
User Interface | 2016-12-14 | 2016-12-19 | 6
Planning and Approval | 2016-12-20 | 2016-12-24 | 5
Sales
Job Order | 2016-12-22 | 2016-12-24 | 2 | Din
Job Elements | 2016-12-26 | 2016-12-29 | 3 | Din
Job Request | 2016-12-31 | 2017-01-02 | 2 | Din
Delivery and Packing | 2017-01-03 | 2017-01-05 | 2 | Din
Upload File | 2017-01-06 | 2019-01-09 | 2 | Din
Sales Estimate | 2017-01-10 | 2017-01-13 | 3 | Din
Quotation | 2017-01-14 | 2017-01-17 | 2 | Din
Document Monitoring | 2017-01-07 | 2017-01-09 | 2 | Gin
Dashboard | 2017-01-16 | 2017-01-18 | 2 | Gin
CAD
Planner Module | 2017-01-18 | 2017-01-20 | 2 | Din
Cost Estimate | 2017-01-21 | 2017-01-24 | 3 | Din
Dashboard - BOM | 2017-01-19 | 2017-01-21 | 1 | Gin
BOM Creation | 2017-01-25 | 2017-01-25 | 1 | Din
Material Creation | 2017-01-26 | 2017-01-26 | 1 | Din
Job Out Creation | 2017-01-27 | 2017-01-27 | 1 | Din
Document Monitoring | 2017-01-10 | 2017-01-10 | 1 | Gin
Dashboard - Estimation | 2017-01-23 | 2017-01-25 | 2 | Gin
Logistic
Dashboard | 2017-01-26 | 2017-01-27 | 2 | Gin
Delivery Preparation | 2017-01-28 | 2017-01-30 | 2 | Din
Delivery Posting | 2017-01-31 | 2017-02-01 | 2 | Din
Document Monitoring | 2017-01-11 | 2017-01-11 | 1 | Gin
Warehouse
Dashboard | 2017-01-28 | 2017-01-30 | 2 | Gin
BOM Issuance | 2017-02-02 | 2017-02-04 | 2 | Din
BOM Issuance Summary (balance monitoring) | 2017-02-06 | 2017-02-06 | 1 | Din
PR to PO (BPR & OPR) | 2017-02-07 | 2017-02-10 | 3 | Din
Transfer Order | 2017-02-11 | 2017-02-11 | 1 | Din
Special Request | 2017-02-13 | 2017-02-13 | 1 | Din
Items | 2017-02-14 | 2017-02-16 | 2 | Din
Document Monitoring | 2017-01-12 | 2017-01-12 | 1 | Gin
Accounting
Dashboard | 2017-01-31 | 2017-02-01 | 2 | Gin
Billing(Sales Invoice, Billing Invoice, Statement of Account) | 2017-02-07 | 2017-02-20 | 2 | Din
Billing Prints | 2017-02-21 | 2017-02-21 | 1 | Din
STF | 2017-02-22 | 2017-02-24 | 2 | Din
Credit Memo | 2017-02-25 | 2017-02-25 | 1 | Din
Outstanding Balance | 2017-02-27 | 2017-02-27 | 1 | Din
Budget monitoring | 2017-02-28 | 2017-03-01 | 2 | Din
Incidental Charges | 2017-03-03 | 2017-03-03 | 1 | Din
Item Journal Adjustment | 2017-03-04 | 2017-03-04 | 1 | Din
Physical Inventory Adjustment | 2017-03-06 | 2017-03-06 | 1 | Din
Document Monitoring | 2017-01-13 | 2017-01-13 | 1 | Gin
Purchasing
Dashboard | 2017-02-02 | 2017-02-03 | 2 | Gin
PO Preparation | 2017-03-07 | 2017-03-09 | 2 | Din
PO Posting | 2017-03-10 | 2017-03-10 | 1 | Din
Management
Dashboard | 2017-02-04 | 2017-02-06 | 2 | Gin
Sales Target | 2017-03-11 | 2017-03-13 | 2 | Din
Free Item Approval | 2017-03-14 | 2017-03-14 | 1 | Din
Request Approval | 2017-03-15 | 2017-03-15 | 1 | Din
PO Approval | 2017-03-16 | 2017-03-16 | 1 | Din
SRP Approval | 2018-03-17 | 2017-03-18 | 2 | Din
Artwork Cost | 2017-03-20 | 2017-03-21 | 1 | Din
Tier | 2017-03-22 | 2017-03-24 | 2 | Din
Document Monitoring | 2017-01-14 | 2017-01-14 | 1 | Gin
HR
Employee | 12/12/2016 - 12/24/2016 |  | 2 Weeks | Gin
Employee Position |  |  |  | Gin
Maintenance |  |  |  | Gin
Machine Mode of Operations |  |  |  | Gin
Machine |  |  |  | Gin
Machine Type |  |  |  | Gin
GL Accounts |  |  |  | Gin
Job Type |  |  |  | Gin
PR Category |  |  |  | Gin
PR Type_Department |  |  |  | Gin
PR Type |  |  |  | Gin
Additional BOM Category |  |  |  | Gin
Picture Category |  |  |  | Gin
Product Category_Sub Category_Instructions |  |  |  | Gin
Packing Instructions |  |  |  | Gin
Sub Category |  |  |  | Gin
Product Category |  |  |  | Gin
Job / Item UOM |  |  |  | Gin
Size UOM |  |  |  | Gin
Payment Terms |  |  |  | Gin
Item Category |  |  |  | Gin
Item Product Category |  |  |  | Gin
Item Product Bracket |  |  |  | Gin
Item Product Price Bracket |  |  |  | Gin
Section |  |  |  | Gin
Transaction Type |  |  |  | Gin
Transaction Purpose |  |  |  | Gin
Purchase Order Status |  |  |  | Gin
Cancelled Category |  |  |  | Gin
Variance Category |  |  |  | Gin
Fixed Asset Type |  |  |  | Gin
Purchase Order_Category |  |  |  | Gin
Purchase Order_Type (Payment Type) |  |  |  | Gin
Purchase Order_Type (Find another term) |  |  |  | Gin
Department |  |  |  | Gin
Bank |  |  |  | Gin
Free Item Category |  |  |  | Gin
Tax Type |  |  |  | Gin
Jobs Request |  |  |  | Gin
Jobs Status |  |  |  | Gin
Jobs Status Rule |  |  |  | Gin
Jobs Request Rule |  |  |  | Gin
Succeedding Jobs Request Category |  |  |  | Gin
Jobs Request Category |  |  |  | Gin
Jobs Request Type |  |  |  | Gin
Jobs Request Status |  |  |  | Gin
Production Document |  |  |  | Gin
Delivery Request |  |  |  | Gin
Production Document_Delivery Request |  |  |  | Gin
Transportation Mode |  |  |  | Gin
Business Unit |  |  |  | Gin
Customer |  |  |  | Gin
Accounts |  |  |  | Gin
User |  |  |  | Gin
Group |  |  |  | Gin
Role |  |  |  | Gin
Vendor |  |  |  | Gin
Resource |  |  |  | Gin
Excess Matrix |  |  |  | Gin
Dashboard Assignment (Position Title?) |  |  |  | Gin
MR Category |  |  |  | Gin
Commision Code |  |  |  | Gin
Business Style |  |  |  | Gin
Reports
PO vs Amount - Report | 12/26/2016 - 01/06/2017 |  | 9 Days | Gin/Din
Job Summary Report - Report |  |  |  | Gin/Din
BOM Issuance Summary (per transaction) - Report |  |  |  | Gin/Din
Free Item |  |  |  | Gin/Din
BOM Search |  |  |  | Gin/Din
Unbilled Delivery Documents |  |  |  | Gin/Din
Jo no PO |  |  |  | Gin/Din
Invoice Aging |  |  |  | Gin/Din
Detailed Sales Report |  |  |  | Gin/Din
Schedule of Sales |  |  |  | Gin/Din
Cash Receipt Book |  |  |  | Gin/Din
Trade Reports |  |  |  | Gin/Din
Accounts Receivable Summary |  |  |  | Gin/Din
Job Stagnant |  |  |  | Gin/Din
Annual Sales - per AE, per Customer |  |  |  | Gin/Din
Sales Report as of 1 Year |  |  |  | Gin/Din
Delivery Billing Summary |  |  |  | Gin/Din
Delivery Summaries |  |  |  | Gin/Din
Delivery Document Search |  |  |  | Gin/Din
Delivery Summary Criteria |  |  |  | Gin/Din
Inconsistent Delivery Report |  |  |  | Gin/Din
Stagnant Documents |  |  |  | Gin/Din
Sample to Production |  |  |  | Gin/Din
Artwork to Production |  |  |  | Gin/Din
Cancelled JO |  |  |  | Gin/Din
Items for QA |  |  |  | Gin/Din
Sales Report |  |  |  | Gin/Din
Unserved Deliveries |  |  |  | Gin/Din
Additional BOM |  |  |  | Gin/Din
FG Inventory |  |  |  | Gin/Din
Quotation Reports |  |  |  | Gin/Din
Asset Valuation by Account Summary |  |  |  | Gin/Din
Project Monitoring |  |  |  | Gin/Din
Uploading Job Order |  |  |  | Gin/Din
Uploading Delivery |  |  |  | Gin/Din
Uploading Elements |  |  |  | Gin/Din
Consolidation of Projects |  |  |  | Gin/Din
List of Purchase Materials that did not move (No Withdrawal) |  |  |  | Gin/Din
Collection Letter |  |  |  | Gin/Din
Credit Memo |  |  |  | Gin/Din
Inventory Ageing Report |  |  |  | Gin/Din
AR Summary |  |  |  | Gin/Din
SRP Report |  |  |  | Gin/Din
Document Type |  |  |  | Gin/Din
Note : additional 1 month for user acceptance(testing and debugging) - up to April 30
Total Modules | Pending Modules | Total Modules Done | No of Modules for review | Percentage Done
Formulas:
Finished Date = [Start Date]+[Days]
Start Date = [Finished Date, row above]+1

## List of Questions
How many developers do we have?
Nakapaglipat na ba sila?
Full time ba yung mga dev?
Pano strategy nila assign/pagawa ng task?
Gano kabilis nilang natatapos ang isang module?
Ano ang kailangan nila sa atin?
Every other day visit